## Slide 1: MPH Report
March 8, 2017

## Slide 2: Updates
Course/Program Revsions
Passed CHHS Curriculum Committee
Passed Graduate Curriculum Committee
Graduate Council: March 9
Student forums: week after spring break
Interim Report
Lots of progress (see interim report update)
Lots to do (see transition timeline update)
Notes: My report this month is brief. Since we last met, the course/program revisions were passed at the CHHS CC and GCC levels. The next level – Grad Council – is March 9th. Assuming all goes well, it should be passed during the senate meeting at the end of the month.
I posted an update on the progress that’s been made toward addressing the deficiencies noted in our self-study. We’ve made a lot progress, but still have a bit of work left to do. I also posted the spring 17 timeline that shows the tasks we’ll be working on over the next few months. Some of these tasks will be done individually, some in committee, and some by the faculty in conjunction with our advisory committee. The really great news is that once we’ve made it through this process, we’ll have transitioned to most of the new criteria.

## Slide 3: Upcoming Tasks: Joint
Create Guiding Statements
Vision: describes how the community/world will be different if the school or program achieves its aims.
Mission Statement: identifies what we will accomplish operationally in our instructional, community engagement and scholarly activities. The mission may also define our setting or community and priority population(s).
Goals: describes strategies to accomplish the defined mission.
Values: informs stakeholders about our core principles, beliefs and priorities.
Develop measures
  Convene assessment committee: March 29
Notes: The next big tasks that we will be doing is creating our guiding statements. I’ve posted a summary document of what is expected and what we have currently. Creating out guiding statements is something that we need to do in conjunction with our advisory committee.
Please note that during the technical assistance webinar, there was a lot of focus on creating meaningful, rather than generic, goals. Ex: Offer a curriculum that prepares students to be effective public health professionals (generic) vs Strengthen student-centered culture and excellence in public health education through an engaging and innovative teaching and learning environment (meaningful).
We will also need to create measures for our goals, which means we need to convene the assessment committee. Volunteers? I’d like to meet at 12:30 on March 29th, please.

## Slide 4: Upcoming Tasks: MPH
Articulate five MPH competencies
  Decide courses to embed for assessment
  Create assessment
Develop procedures/tools for
  ILE
  GrAPEs
Notes: The MPH committee also needs to create at least five competencies. I’ve asked the advisory committee to bring a list of the top ten skills needed by MPH students to the meeting and planned on doing a process like we did during the workday. We can list and ours, we’ll be able to craft the competencies from our combined lists.
We also need to develop procedures and tools to effectuate the recommendations for ILEs and GrAPEs that we end up passing today.

## Slide 5: Upcoming Tasks: Individual
Align courses with competencies (including ones we develop) and foundational knowledge (if applicable)
Common learning objectives/competency alignments/assessment for core courses with multiple instructors
Revise syllabi
Notes: Last, once we’ve developed the new competencies, we all need to, individually, start working on our individual courses to make them align more seamlessly with all of the competencies (CEPH’s and ours). For core classes where there is more than one instructor, please collaborate and make sure the same competencies about being addressed and same competency assessment is being used.
We will then also need to work on revising our syllabi. I’m still working on creating a prototype and plan to present it when the MPH curriculum committee meets later this semester (April 19th)

## Slide 6: Save the Dates
March 24, 10 – 2:30: External Advisory Com.
March 29, 12:30 – 2:30: Assessment Com.
April 5, 12:30 – 2:30: Joint MPH-BSPH
April 11-13: KPHA
April 19, 12:30 – 2:30: MPH Curriculum Com.
April 26, 12:30 – 2:30: ILE/APE ad hocs
May 3, 12:30 – 2:30: Diversity ad hoc
May 10: 12:30 – 2:30: Joint MPH-BSPH